## Projected
|  | 25th Jun | 28th Jun - 30th Jul | 2nd Aug - 27th Aug | 3rd Sep - 24th Sep | 1st Oct | 8th Oct | 15th Oct | 22nd Oct | 29th Oct | 5th Nov | 12th Nov | 19th Nov | 26th Nov | 3rd Dec | 10th Dec | 17th Dec | 24th Dec | 31st Dec | 7th Jan | 14th Jan | 21st Jan | 28th Jan | 4th Feb | 11th Feb | 18th Feb | 25th Feb | 4th Mar | 11th Mar | 18th Mar | 25th Mar | 1st Apr | 8th Apr | 15th Apr | 22nd Apr | 29th Apr | 6th May | 13th May | 20th May | 27th May | 31st May
WP | Task | WK 1 | WK 2 - 6 | WK 7 - 10 | WK 11 - 14 | WK 15 | WK 16 | WK 17 | WK 18 | WK 19 | WK 20 | WK 21 | WK 22 | WK 23 | WK 24 | WK 25 | WK 26 | WK 27 | WK 28 | WK 29 | WK 30 | WK 31 | WK 32 | WK 33 | WK 34 | WK 35 | WK 36 | WK 37 | WK 38 | WK 39 | WK 40 | WK 41 | WK 42 | WK 43 | WK 44 | WK 45 | WK 46 | WK 47 | WK 48 | WK 49 | WK 50
Report
Create an account
Load template
Read guidelines
Deliverables
Updates with Mentor | bar: 1st Oct WK 15 to 8th Oct WK 16; 22nd Oct WK 18 to 17th Dec WK 26; 7th Jan WK 29 to 28th Jan WK 32; 11th Feb WK 34 to 25th Mar WK 40; 15th Apr WK 43 to 31st May WK 50
Record prototype and results | bar: 14th Jan WK 30 to 25th Feb WK 36
Upload VIVA | bar: 31st May WK 50
Submit report | bar: 27th May WK 49
Research Methodology
Hypothesis | bar: 3rd Dec WK 24 to 10th Dec WK 25
Research Questions | bar: 3rd Dec WK 24 to 10th Dec WK 25
Research Methods | bar: 3rd Dec WK 24 to 24th Dec WK 27
Explain prototype | bar: 31st Dec WK 28 to 7th Jan WK 29
Validty of research | bar: 7th Jan WK 29
Research Pipeline | bar: 7th Jan WK 29
Finalise section in report | bar: 22nd Apr WK 44 to 29th Apr WK 45
Literature Review
Research papers related to the area of study | bar: 1st Oct WK 15 to 29th Oct WK 19
Review basic terminology related to the are of study | bar: 15th Oct WK 17 to 22nd Oct WK 18
Review datasets | bar: 29th Oct WK 19 to 5th Nov WK 20
Review Different approaches | bar: 29th Oct WK 19 to 12th Nov WK 21
Review different evaluation metrics | bar: 12th Nov WK 21 to 26th Nov WK 23
Finalise section in report | bar: 22nd Apr WK 44 to 29th Apr WK 45
Prototype
Find tutorial
Replicate tutorial
Create custom dataset
Tweek prototype
Generate evaluation results
Discussion of Results
Write prototype evaluation | bar: 25th Feb WK 36 to 11th Mar WK 38
Write dataset evaluation | bar: 18th Mar WK 39 to 25th Mar WK 40
Write hypothesis testing | bar: 1st Apr WK 41
Compare results after finetuning dataset | bar: 8th Apr WK 42
Write project evaluation | bar: 8th Apr WK 42 to 15th Apr WK 43
Finalise section in report
Other sections (Conclusion, Introduction, Abstract)
Finalise conclusion & recommendations | bar: 6th May WK 46
Finalise Introduction | bar: 13th May WK 47
Finalise Abstract | bar: 20th May WK 48
Review Project

## Actual
|  | 25th Jun | 28th Jun - 30th Jul | 2nd Aug - 27th Aug | 3rd Sep - 24th Sep | 1st Oct | 8th Oct | 15th Oct | 22nd Oct | 29th Oct | 5th Nov | 12th Nov | 19th Nov | 26th Nov | 3rd Dec | 10th Dec | 17th Dec | 24th Dec | 31st Dec | 7th Jan | 14th Jan | 21st Jan | 28th Jan | 4th Feb | 11th Feb | 18th Feb | 25th Feb | 4th Mar | 11th Mar | 18th Mar | 25th Mar | 1st Apr | 8th Apr | 15th Apr | 22nd Apr | 29th Apr | 6th May | 13th May | 20th May | 27th May | 31st May
WP | Task | WK 1 | WK 2 - 6 | WK 7 - 10 | WK 11 - 14 | WK 15 | WK 16 | WK 17 | WK 18 | WK 19 | WK 20 | WK 21 | WK 22 | WK 23 | WK 24 | WK 25 | WK 26 | WK 27 | WK 28 | WK 29 | WK 30 | WK 31 | WK 32 | WK 33 | WK 34 | WK 35 | WK 36 | WK 37 | WK 38 | WK 39 | WK 40 | WK 41 | WK 42 | WK 43 | WK 44 | WK 45 | WK 46 | WK 47 | WK 48 | WK 49 | WK 50
Report
Create an account
Load template
Read guidelines
Deliverables
| Updates with mentor |  |  |  |  | 3rd Dec WK 24: *Was not able to meet mentor as frequentyl as antispiated due to issues with timing and availblilty of lecturer
Record prototype and results | bar: 28th Jan WK 32 to 11th Mar WK 38
Upload VIVA | bar: 31st May WK 50
Submit report | bar: 27th May WK 49
Research Methodology
| Hypothesis |  |  |  |  | 17th Dec WK 26: * Work was delayed due to exams and assignments
Research Questions | bar: 3rd Dec WK 24 to 10th Dec WK 25
Research Methods | bar: 3rd Dec WK 24 to 10th Dec WK 25; 21st Jan WK 31 to 28th Jan WK 32
Explain prototype | bar: 4th Feb WK 33 to 11th Feb WK 34
Validty of research | bar: 11th Feb WK 34
Research Pipeline | bar: 11th Feb WK 34
Finalise section in report | bar: 6th May WK 46
Literature Review
| Research papers related to the area of study |  |  | * | Work was delayed as SOI needed to be arranged | bar: 8th Oct WK 16 to 29th Oct WK 19
Review basic terminology related to the are of study | bar: 15th Oct WK 17 to 22nd Oct WK 18
Review datasets | bar: 29th Oct WK 19 to 5th Nov WK 20
Review Different approaches | bar: 29th Oct WK 19 to 12th Nov WK 21
Review different evaluation metrics | bar: 12th Nov WK 21 to 26th Nov WK 23
Finalise section in report | bar: 6th May WK 46
Prototype
Find tutorial
Replicate tutorial
Create custom dataset
Tweek prototype
Generate evaluation results
Discussion of Results
Write prototype evaluation | bar: 18th Mar WK 39 to 25th Mar WK 40
Write dataset evaluation | bar: 18th Mar WK 39 to 25th Mar WK 40
Write hypothesis testing | bar: 1st Apr WK 41
Compare results after finetuning dataset | bar: 8th Apr WK 42
Write project evaluation | bar: 8th Apr WK 42 to 15th Apr WK 43
Finalise section in report
Other sections (Conclusion, Introduction, Abstract)
Finalise conclusion & recommendations | bar: 6th May WK 46
Finalise Introduction | bar: 13th May WK 47
Finalise Abstract | bar: 20th May WK 48
Review Project